## 문서변경이력
에코비트 사이트 리뉴얼 _국/영
Work Breakdown Structure history
버전_작성일 | 변경이력 | 작성자 | 비고
v0.1_20211215 | 1차 작성 | 노희영
v0.2_20211220 | 2차 작성(계약일 변경) | 노희영
v0.3_20211227 | 3차 작성 | 김이래
v0.4_20220106 | 4차 작성(영문번역 기간변경) | 김이래
v0.5_20220111 | 5차 작성 구축일정 시트 추가 | 노희영
v1.0_20220119 | 전체 일정 수정 | 봉윤경
v1.1_20220203 | 전체일정표 시트 수정 | 김이래

## 구축일정 (hidden)
|  | 1월 |  |  |  | 2월 |  |  |  | 3월 |  |  |  |  | 4월
|  | 1주 | 2주 | 3주 | 4주 | 1주 | 2주 | 3주 | 4주 | 1주 | 2주 | 3주 | 4주 | 5주 | 1주 | 2주 | 3주 | 4주 | 5주
분석 | bar: 1월 1주 to 1월 2주
자료수집 | bar: 1월 1주 to 1월 4주
기획 | 국문_WEB,TA | bar: 1월 2주 to 1월 3주
국문_MO | bar: 1월 3주 to 1월 4주
영문_WEB,TA | bar: 1월 4주
영문_MO | bar: 1월 4주
디자인 | 국문_WEB,TA | bar: 1월 3주 to 2월 3주
국문_MO | bar: 2월 2주 to 2월 4주
영문_WEB,TA | bar: 2월 4주 to 3월 2주
영문_MO | bar: 3월 1주 to 3월 3주
퍼블리싱 | 국문_WEB,TA | bar: 1월 4주 to 3월 1주
국문_MO
영문_WEB,TA | bar: 3월 2주 to 3월 4주
영문_MO
개발 | bar: 2월 3주 to 4월 3주
단위테스트 | bar: 3월 4주 to 4월 1주
종합테스트 | bar: 4월 2주 to 4월 4주
사이트 오픈 |  | 4월 5주: 25일

## 보고_공정표 (hidden)
Criteria | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29
Plan | 4.54% | 4.6% | 5.04% | 6.71% | 9.23% | 12.65% | 12.83% | 13.96% | 16.14% | 18.02% | 18.04%
Completion | 3.28% | 4.11% | 4.33% | 4.48% | 7.16% | 7.97% | 8.9% | 10.31% | 14.11% | 11.68% | 12.77%
| 12월 3주 | 4주 | 1월 1주 | 2주 | 3주 | 4주 | 5주 | 2월 1주 | 2주 | 3주 | 4주 | 3월 1주 | 2주 | 3주 | 4주 | 4월 1주 | 2주 | 3주 | 4주 | 5주 | 5월 1주 | 2주 | 3주 | 4주 | 6월 1주 | 2주 | 3주 | 4주 | 7월1주
Initiating
Analytic
Desig
Closing
Testing
Developing

## 전체일정표
l 사
에코비트 리뉴얼
Work Breakdown Structure
v0.5_20220111
Project period : 2022.01.10 ~ 2022.04.25 (총 4.5개월)
일정 지연
단계 | 활동 | 구분 | 2021.12 |  |  |  | 2022.01 |  |  |  | 2022.02 |  |  |  | 2022.03 |  |  |  |  | 2022.04 |  |  |  | 2022.05
|  |  | 1주 | 2주 | 3주 | 4주 | 1주 | 2주 | 3주 | 4주 | 1주 | 2주 | 3주 | 4주 | 1주 | 2주 | 3주 | 4주 | 5주 | 1주 | 2주 | 3주 | 4주 | 1주 | 2주
계획 | WBS | bar: 2021.12 2주
분석 | 요구사항, IA,시스템 | bar: 2021.12 2주; 2022.01 2주 to 2022.02 1주
설계 | 기획_화면설계 | kr_PC/MO | bar: 2022.01 2주 to 2022.02 2주
en_PC/MO | bar: 2022.02 2주 to 2022.02 3주
번역 | bar: 2022.02 1주 to 2022.02 2주
admin | bar: 2022.02 1주 to 2022.02 2주
| 디자인 | kr_PC/MO | bar: 2022.02 1주 to 2022.02 3주
en_PC/MO | bar: 2022.02 4주 to 2022.03 2주
| 퍼블리싱 | kr_PC/MO | bar: 2022.02 2주 to 2022.03 1주
en_PC/MO | bar: 2022.03 2주 to 2022.03 5주
| 개발 | kr_front | bar: 2022.03 2주 to 2022.04 1주
en_front | bar: 2022.03 5주 to 2022.04 2주
back-end | bar: 2022.02 4주 to 2022.04 1주
테스트 | 시나리오,단위,통합 | bar: 2022.03 1주 to 2022.04 3주
보고 | 중간보고 | bar: 2022.02 2주
완료보고 | bar: 2022.05 1주
오픈 | bar: 2022.04 4주

## WBS 통합
에코비트 리뉴얼 | [13 empty] | 01월 2주차 공정률
Work Breakdown Structure |  |  |  | ■ 기획 | ■ 테스트 | [8 empty] | 계획 | 72.99% |  | 실적 | 0.35%
v0.5_20220111 |  |  |  | ■ 디자인 | ■ 보고/오픈
Project period : 2022.01.10 ~ 2022.04.25 (총 4.5개월) |  |  |  | ■ 퍼블리싱 | 영문
■ 개발
[20 empty] | 2021.12 | [30 empty] | 2022.01 | [30 empty] | 2022.02 | [27 empty] | 2022.03 | [30 empty] | 2022.04 | [29 empty] | 2022.05
단계 | 활동 | Task |  |  | 담당자 | 상태 | 누적실적관리 |  |  | 일정관리 |  |  | 비고 | 단계별 비중업무 | 전체 내 비중업무 | 계획 |  | 실적 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7
|  | 구분1 | 구분2 | 구분3 |  |  | 전체본수 | 예상본수 | 최종본수 | 시작예정일 | 종료예정 | 종료일 |  |  |  | 목료완료율 | 환산율 | 실제완료율 | 환산율
계획 | 1%
| 계약진행 | 계약 |  |  | 그룹 / 기획 | 진행중 | 1 | 1 | 0 |  |  | 2022-01-10 |  | 40% | 0.4% | 100% | 0.4% | 0% | 0%
| 일정 계획 | 일정표 작성(WBS) |  |  | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-10 | 2022-01-11 | 2022-01-19 |  | 40% | 0.4% | 100% | 0.4% | 0% | 0% | bar: 2021.12 2 to 2021.12 3
| 프로젝트 런칭 | Kick off |  |  |  | 진행중 | 1 | 1 | 0 | 2022-01-11 | 2022-01-11 | 2022-01-11 |  | 20% | 0.2% | 100% | 0.2% | 0% | 0% | bar: 2021.12 6; 2022.01 11
소계 | [6 empty] | 3 | 3 | 0 |  |  |  |  | 100% | 1% | 100% | 1% | 0% | 0%
분석 | 5%
| 기획 정의 | 인터뷰 및 요구사항 정의 |  |  | 기획 | 진행중 | 1 | 1 | 0 | 2021-12-10 | 2022-01-28 |  |  | 20% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.01 11 to 2022.01 14; 2022.01 17 to 2022.01 21; 2022.01 24 to 2022.01 28
|  | 정보구조(IA) / 레이블링 정의 (PC&Mobile Web/Language) |  |  | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-11 | 2022-01-28 |  |  | 15% | 1% | 100% | 1% | 0% | 0% | bar: 2022.01 11 to 2022.01 14; 2022.01 17 to 2022.01 20; 2022.01 24 to 2022.01 28
| 디자인 정의 | 벤치 |  |  | 디자이너 | 진행중 | 1 | 1 | 0 | 2022-01-11 | 2022-01-21 |  |  | 15% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.01 11 to 2022.01 14
|  | 디자인 시안 컨펌 |  |  | 디자이너 | 진행중 | 1 | 1 | 0 | 2022-01-10 | 2022-01-25 |  |  | 15% | 1% | 100% | 1% | 0% | 0% | bar: 2022.01 17 to 2022.01 21; 2022.01 24 to 2022.01 25
| 개발정의 | 시스템 환경 분석 |  |  |  | 진행중 | 1 | 1 | 0 | 2022-02-03 | 2022-02-14 |  |  | 15% | 0.75% | 100% | 0.75% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 10; 2022.02 14
|  | 개발 서버 환경 정의 |  |  |  | 진행중 | 1 | 1 | 0 | 2022-02-03 | 2022-02-14 |  |  | 10% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 10; 2022.02 14
|  | 개발 서버 세팅 |  |  |  | 진행중 | 1 | 1 | 0 | 2022-02-03 | 2022-02-14 |  |  | 10% | 0.75% | 100% | 0.75% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 10; 2022.02 14
소계 | [6 empty] | 7 | 7 | 0 |  |  |  |  | 100% | 5% | 100% | 5% | 0% | 0%
설계 | 35%
| 기획 설계 | 정보구조(IA) / 레이블링 확정 |  |  | 기획/에코비트 | 진행중 | 1 | 1 | 0 | 2022-01-11 | 2022-01-28 |  |  | 3% | 1.05% | 100% | 1.05% | 0% | 0% | bar: 2022.01 11 to 2022.01 14; 2022.01 17 to 2022.01 21; 2022.01 24 to 2022.01 28
화면설계 작성(PC - 한국어) | bar: 2022.05 1 to 2022.05 7
|  |  | Main |  | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-11 | 2022-01-12 |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0% | bar: 2022.01 11 to 2022.01 12
|  |  | 회사소개 | 인사말 | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 기업비전 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% |  |  | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | CI | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% |  |  | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 인재상 | 기획 | 진행중 | 3 | 3 | 3 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | 100% | 0.35% | 100% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 자회사소개 | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 연혁 | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 오시는 길 | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  | 사업소개 | 워터 BU | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 에너지 BU | 기획 | 진행중 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 그린 BU | 기획 | 진행중 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 미래사업 BU | 기획 | 진행중 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 기술분야 | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  | ESG경영 | 환경경영 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 컴플라이언스 경영 | 기획 | 예정 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 안전경영 | 기획 | 예정 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 지배구조 | 기획 | 예정 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 지속가능경영보고서 | 기획 | 예정 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  | 투자정보 | 공고 | 기획 | 진행중 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 공시정보 | 기획 | 진행중 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | IR자료실 | 기획 | 진행중 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  | 미디어센터 | 보도자료 | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 홍보자료 | 기획 | 진행중 | 1 | 1 |  | 2022-01-12 | 2022-01-21 |  |  | 1% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  |  |  | 유튜브 | 기획 | 진행중 | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 12 to 2022.01 14; 2022.01 17 to 2022.01 21
|  | 화면설계 작성(Mobile Web - 한국어) | Main |  | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0% | bar: 2022.01 24 to 2022.01 28
|  |  | 회사소개 | 인사말 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 기업비전 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | CI | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 인재상 | 기획 | 예정 | 3 | 3 | 3 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 자회사소개 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 연혁 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 오시는 길 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  | 사업소개 | 워터 BU | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 에너지 BU | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 그린 BU | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 미래사업 BU | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 기술분야 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  | ESG경영 | 환경경영 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 컴플라이언스 경영 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 안전경영 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 지배구조 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 지속가능경영보고서 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  | 투자정보 | 공고 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 공시정보 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | IR자료실 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  | 미디어센터 | 보도자료 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 홍보자료 | 기획 | 예정 | 1 | 1 |  | 2022-01-24 | 2022-01-27 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 24 to 2022.01 28
|  |  |  | 유튜브 | 기획 | 예정 | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.01 24 to 2022.01 28
|  | 영문 번역 |  |  | 펜타브리드 | 예정 | 1 | 1 | 0 | 2022-02-03 | 2022-02-19 |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
화면설계 작성(PC - 영문)
|  |  | Main |  | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 회사소개 | 인사말 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기업비전 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | CI | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 인재상 | 기획 | 예정 | 3 | 3 | 3 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 자회사소개 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 연혁 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 오시는 길 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 사업소개 | 워터 BU | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 에너지 BU | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 그린 BU | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 미래사업 BU | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기술분야 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | ESG경영 | 환경경영 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 컴플라이언스 경영 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 안전경영 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지배구조 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지속가능경영보고서 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 투자정보 | 공고 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 공시정보 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | IR자료실 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 미디어센터 | 보도자료 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 홍보자료 | 기획 | 예정 | 1 | 1 |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 유튜브 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  | 화면설계 작성(Mobile Web- 영문) | Main |  | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 회사소개 | 인사말 | 기획 | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기업비전 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | CI | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 인재상 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 자회사소개 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 연혁 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 오시는 길 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 사업소개 | 워터 BU | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 에너지 BU | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 그린 BU | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 미래사업 BU | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기술분야 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | ESG경영 | 환경경영 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 컴플라이언스 경영 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 안전경영 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지배구조 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지속가능경영보고서 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 투자정보 | 공고 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 공시정보 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | IR자료실 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 미디어센터 | 보도자료 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 홍보자료 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 유튜브 | 기획 | 예정 |  |  |  | 2022-02-14 | 2022-02-18 |  |  | 1% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
관리자 (통합)
|  |  | 관리자 전체 |  | 기획 | 예정 | 1 | 1 | 0 | 2022-02-03 | 2022-02-18 |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
| 디자인 설계 | 디자인 가이드 작업(PC&Mobile Web) |  |  | 디자이너 | 진행중 | 1 | 1 | 0 |  |  |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0% | bar: 2022.01 26 to 2022.01 28
| 퍼블리싱 설계 | 퍼블리싱 가이드 정의(PC&Mobile Web) |  |  | 퍼블리셔 | 예정 | 1 | 1 | 0 |  |  |  |  | 2% | 0.7% | 100% | 0.7% | 0% | 0%
소계 | [5 empty] | 진행중 | 85 | 85 | 9 |  |  |  |  | 111% | 14% | 100% | 10.5% | 4.545% | 0.35%
구현 | 50%
디자인
|  | 디자인 가이드(PC&Mobile Web) |  |  |  | 예정 | 8 | 8 | 0 |  |  |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.01 26 to 2022.01 28
메뉴별 디자인(PC - 한국어)
|  |  | GNB MENU |  |  | 예정 | 1 | 1 | 0 | 2022-02-03 | 2022-02-18 |  |  | 1.5% | 0.75% | 100% | 0.75% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  | Main |  | 허은영 | 예정 | 1 | 1 | 0 | 2022-02-03 | 2022-02-18 |  |  | 1.5% | 0.75% | 100% | 0.75% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  | 회사소개 | 인사말 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 기업비전 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | CI | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 1; 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 인재상 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 자회사소개 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 연혁 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 오시는 길 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  | 사업소개 | 워터 BU | 양정민/서상근 | 예정 | 1 | 1 | 0 |  | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 에너지 BU | 양정민/서상근 | 예정 | 1 | 1 | 0 |  | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 그린 BU | 양정민/서상근 | 예정 | 1 | 1 | 0 |  | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 미래사업 BU | 양정민/서상근 | 예정 | 1 | 1 | 0 |  | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 기술분야 | 양정민/서상근 | 예정 | 1 | 1 | 0 |  | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  | ESG경영 | 환경경영 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 컴플라이언스 경영 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 안전경영 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 지배구조 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 지속가능경영보고서 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-09 | 2022-02-18 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  | 투자정보 | 공고 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-04 | 2022-02-08 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 공시정보 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-04 | 2022-02-08 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | IR자료실 | 양정민 | 예정 | 1 | 1 | 0 | 2022-02-04 | 2022-02-08 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  | 미디어센터 | 보도자료 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-04 | 2022-02-08 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 홍보자료 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-04 | 2022-02-08 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 3 to 2022.02 4; 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18
|  |  |  | 유튜브 | 서상근 | 예정 | 1 | 1 | 0 | 2022-02-04 | 2022-02-08 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | 2022.01 6: 0; 2022.02 3: ■; 2022.02 4: ■; 2022.02 7: ■; 2022.02 8: ■; 2022.02 9: ■; 2022.02 10: ■; 2022.02 11: ■; 2022.02 14: ■; 2022.02 15: ■; 2022.02 16: ■; 2022.02 17: ■; 2022.02 18: ■
|  | 메뉴별 디자인(Mobile Web - 한국어) | Main |  |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 회사소개 | 인사말 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기업비전 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | CI |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 인재상 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 자회사소개 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 연혁 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 오시는 길 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 사업소개 | 워터 BU |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 에너지 BU |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 그린 BU |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 미래사업 BU |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기술분야 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | ESG경영 | 환경경영 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 컴플라이언스 경영 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 안전경영 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지배구조 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지속가능경영보고서 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 투자정보 | 공고 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 공시정보 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | IR자료실 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 미디어센터 | 보도자료 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 홍보자료 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 유튜브 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
메뉴별 디자인(PC - 영문)
|  |  | GNB MENU |  |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | Main |  |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 회사소개 | 인사말 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 기업비전 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | CI |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 인재상 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 자회사소개 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 연혁 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 오시는 길 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 사업소개 | 워터 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 에너지 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 그린 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 미래사업 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 기술분야 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | ESG경영 | 환경경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 컴플라이언스 경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 안전경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 지배구조 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 지속가능경영보고서 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 투자정보 | 공고 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 공시정보 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | IR자료실 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 미디어센터 | 보도자료 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 홍보자료 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 유튜브 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
메뉴별 디자인(Mobile Web- 영문)
|  |  | Main |  |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 회사소개 | 인사말 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 기업비전 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | CI |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 인재상 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 자회사소개 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 연혁 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 오시는 길 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 사업소개 | 워터 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 에너지 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 그린 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 미래사업 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 기술분야 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | ESG경영 | 환경경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 컴플라이언스 경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 안전경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.15% | 0.075% | 100% | 0.075% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 지배구조 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.15% | 0.075% | 100% | 0.075% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 지속가능경영보고서 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-15 |  |  | 0.15% | 0.075% | 100% | 0.075% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 투자정보 | 공고 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 공시정보 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | IR자료실 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  | 미디어센터 | 보도자료 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.15% | 0.075% | 100% | 0.075% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 홍보자료 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.15% | 0.075% | 100% | 0.075% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
|  |  |  | 유튜브 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.15% | 0.075% | 100% | 0.075% | 0% | 0% | bar: 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 15
퍼블리싱
|  | 다국어 퍼블리싱 가이드(PC&Mobile Web) |  |  |  | 예정 | 1 | 1 | 0 | 2022-02-04 | 2022-02-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 7 to 2022.02 11; 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  | 메뉴별 퍼블리싱(PC - 한국어) | GNB MENU |  |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | Main |  |  | 예정 | 1 | 1 | 0 | 2022-02-18 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 회사소개 | 인사말 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기업비전 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | CI |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 인재상 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 자회사소개 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 연혁 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 오시는 길 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 사업소개 | 워터 BU |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 에너지 BU |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 그린 BU |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 미래사업 BU |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 기술분야 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | ESG경영 | 환경경영 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 컴플라이언스 경영 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 안전경영 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지배구조 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  |  | 지속가능경영보고서 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18; 2022.02 21 to 2022.02 25
|  |  | 투자정보 | 공고 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18
|  |  |  | 공시정보 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18
|  |  |  | IR자료실 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18
|  |  | 미디어센터 | 보도자료 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18
|  |  |  | 홍보자료 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18
|  |  |  | 유튜브 |  | 예정 | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 0.75% | 0.375% | 100% | 0.375% | 0% | 0% | bar: 2022.02 14 to 2022.02 18
|  | 메뉴별 퍼블리싱(Mobile Web - 한국어) | Main |  |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  | 회사소개 | 인사말 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 기업비전 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | CI |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 인재상 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 자회사소개 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 연혁 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 오시는 길 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  | 사업소개 | 워터 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 에너지 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 그린 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 미래사업 BU |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 기술분야 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  | ESG경영 | 환경경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 컴플라이언스 경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 안전경영 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 지배구조 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  |  | 지속가능경영보고서 |  | 예정 | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4
|  |  | 투자정보 | 공고 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25
|  |  |  | 공시정보 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25
|  |  |  | IR자료실 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25
|  |  | 미디어센터 | 보도자료 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25
|  |  |  | 홍보자료 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25
|  |  |  | 유튜브 |  | 예정 | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.02 21 to 2022.02 25
메뉴별 퍼블리싱(PC - 영문)
|  |  | GNB MENU |  |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  |  | Main |  |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  | 회사소개 | 인사말 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 기업비전 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | CI |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 인재상 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 자회사소개 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 연혁 |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  |  |  | 오시는 길 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  | 사업소개 | 워터 BU |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 에너지 BU |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 그린 BU |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 미래사업 BU |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 기술분야 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  | ESG경영 | 환경경영 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 컴플라이언스 경영 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 안전경영 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 지배구조 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  |  | 지속가능경영보고서 |  | 예정 | 1 | 1 | 0 | 2022-03-14 | 2022-03-18 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 14 to 2022.03 18
|  |  | 투자정보 | 공고 |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  |  |  | 공시정보 |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  |  |  | IR자료실 |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  |  | 미디어센터 | 보도자료 |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  |  |  | 홍보자료 |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  |  |  | 유튜브 |  | 예정 | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11
|  | 메뉴별 퍼블리싱(Mobile Web- 영문) | Main |  |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-04-01 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 21 to 2022.03 25; 2022.03 28 to 2022.04 1
|  |  | 회사소개 | 인사말 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 기업비전 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | CI |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 인재상 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 자회사소개 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 연혁 |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-03-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 21 to 2022.03 25
|  |  |  | 오시는 길 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  | 사업소개 | 워터 BU |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 에너지 BU |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.25% | 0.125% | 100% | 0.125% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 그린 BU |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.24% | 0.12% | 100% | 0.12% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 미래사업 BU |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.2% | 0.1% | 100% | 0.1% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 기술분야 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  | ESG경영 | 환경경영 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 컴플라이언스 경영 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 안전경영 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 지배구조 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  |  | 지속가능경영보고서 |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-01 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 28 to 2022.04 1
|  |  | 투자정보 | 공고 |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-03-25 | bar: 2022.03 21 to 2022.03 25
|  |  |  | 공시정보 |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-03-25 | bar: 2022.03 21 to 2022.03 25
|  |  |  | IR자료실 |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-03-25 | bar: 2022.03 21 to 2022.03 25
|  |  | 미디어센터 | 보도자료 |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-03-25 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 21 to 2022.03 25
|  |  |  | 홍보자료 |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-03-25 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 21 to 2022.03 25
|  |  |  | 유튜브 |  | 예정 | 1 | 1 | 0 | 2022-03-21 | 2022-03-25 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0% | bar: 2022.03 21 to 2022.03 25
개발
|  | Front-end 개발_국문 |  |  |  | 예정 | 5 | 5 | 0 | 2022-03-10 | 2022-04-08 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 18; 2022.03 21 to 2022.03 25; 2022.03 28 to 2022.04 1; 2022.04 4 to 2022.04 8
|  | Front-end 개발_영문 |  |  |  | 예정 | 5 | 5 | 0 | 2022-03-28 | 2022-04-15 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.03 28 to 2022.04 1; 2022.04 4 to 2022.04 8; 2022.04 11 to 2022.04 15
|  | Back-end 개발 |  |  | 개발 | 예정 | 8 | 8 | 0 | 2022-02-21 | 2022-04-15 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.02 21 to 2022.02 25; 2022.02 28; 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 18; 2022.03 21 to 2022.03 25; 2022.03 28 to 2022.04 1; 2022.04 4 to 2022.04 8; 2022.04 11 to 2022.04 15
소계 | [6 empty] | 215 | 215 | 0 |  |  |  |  | 97.99% | 48.99% | 100% | 49% | 0% | 0%
테스트/검수 | 5%
| 테스트 | 테스트 시나리오 작성_국문/영문 |  |  |  | 예정 | 1 | 1 | 0 | 2022-03-01 | 2022-03-18 |  |  | 5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 18
|  | 테스트 시나리오 작성_관리자 |  |  |  | 예정 | 1 | 1 | 0 | 2022-03-01 | 2022-03-18 |  |  | 5% | 0.25% | 100% | 0.25% | 0% | 0% | bar: 2022.03 2 to 2022.03 4; 2022.03 7 to 2022.03 8; 2022.03 10 to 2022.03 11; 2022.03 14 to 2022.03 18
|  | 단위 테스트 |  |  |  | 예정 | 1 | 1 | 0 | 2022-03-28 | 2022-04-15 |  |  | 20% | 1% | 100% | 1% | 0% | 0% | bar: 2022.03 21 to 2022.03 25; 2022.03 28 to 2022.04 1; 2022.04 4 to 2022.04 8; 2022.04 11 to 2022.04 15
|  | 통합 테스트 |  |  |  | 예정 |  |  |  | 2022-04-18 | 2022-04-22 | bar: 2022.04 18 to 2022.04 22
|  | 디버깅/수정 |  |  |  | 예정 | 1 | 1 | 0 | 2022-04-04 | 2022-04-22 |  |  | 10% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2022.04 4 to 2022.04 8; 2022.04 11 to 2022.04 15; 2022.04 18 to 2022.04 22
소계 | [6 empty] | 4 | 4 | 0 |  |  |  |  | 40% | 2% | 100% | 2% | 0% | 0%
완료 | 4%
| 오픈 | 오픈 (2022.04.25) |  |  |  | 예정 | 1 | 1 | 0 | 2022-04-25 | 2022-04-25 |  |  | 20% | 0.8% | 100% | 0.8% | 0% | 0% | bar: 2022.04 25
| 보고 | 중간보고 |  |  | 기획 | 예정 | 1 | 1 | 0 | 2022-02-15 | 2022-02-15 |  |  | 5% | 0.2% | 100% | 0.2% | 0% | 0% | bar: 2022.02 15; 2022.04 26 to 2022.04 29; 2022.05 1 to 2022.05 4; 2022.05 6
|  | 완료보고 |  |  | 기획 | 예정 | 1 | 1 | 0 | 2022-05-05 | 2022-05-06 |  |  | 10% | 0.4% | 100% | 0.4% | 0% | 0% | bar: 2022.05 6
| 산출물 제작 | 완료 산출물 / 제출 |  |  | 기획/개발/디자인/퍼블리싱 | 예정 | 5 | 5 | 0 | 2022-04-26 | 2022-05-06 |  |  | 5% | 0.2% | 100% | 0.2% | 0% | 0% | bar: 2022.04 26 to 2022.04 29; 2022.05 1 to 2022.05 4; 2022.05 6
| 안정화 | 안정화 |  |  | 기획/개발/디자인/퍼블리싱 | 예정 | 1 | 1 | 0 | 2022-04-26 | 2022-05-06 |  |  | 10% | 0.4% | 100% | 0.4% | 0% | 0% | bar: 2022.04 26 to 2022.04 29; 2022.05 1 to 2022.05 4; 2022.05 6
소계 | [6 empty] | 9 | 9 | 0 |  |  |  |  | 50% | 2% | 100% | 2% | 0% | 0%
공정율 합계 | [13 empty] | 72.99% |  | 69.5% |  | 0.35% |  | 2022.04 2: #REF!; 2022.04 4: #REF!; 2022.04 6: #REF!
Note on N11: 봉 윤경: 담당자 교체로 인한 3주 홀딩 변경 계약서 작성
Note on O13: 봉 윤경: 1/11 전임 담당자 출산휴가로 변경 하여 약식 킥오프 진행
Note on AA13: 봉 윤경: 1차 킥오프 이아람 선임
Note on BK13: 봉 윤경: 2차 킥오프 최수아 사원
Note on CT349: 중간보고 메인/서버 디자인 리뷰 및 확정 진행현황 및 향후 일정 리뷰

## WBS_영문 (hidden)
Jeju Dream Tower Web Platform | [12 empty] | 1rd week of March
Work Breakdown Structure | [12 empty] | Plan | #REF! |  | Performance | #REF!
v0.5_20220111
Project period : 2022.01.10 ~ 2022.04.25 (총 4.5개월)
2and Open
[20 empty] | 2019.12 | [30 empty] | 2020.01 | [30 empty] | 2020.02 | [28 empty] | 2020.03 | [30 empty] | 2020.04 | [29 empty] | 2020.05 | [30 empty] | 2020.06 | [29 empty] | 2020.07
Process | Work | Task |  |  | Responsibility | Progress Status | Performance Management |  |  | Calendar |  |  | Note | Importance within the Phase | Importance within the Entire Process | Plan |  | Performance |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  | Activity | Menu | 2nd Open |  |  | Whole number | Estimated number | Final number | Estimated Start Date | Estimated Due Date | Completion Date |  |  |  | Objective Completion Rate | Exchange Rate | Actual Completion Rate | Exchange Rates
Initiating | 1%
| Contract | Contract |  |  | JDT / Planning | Progress | 1 | 1 | 0 | 0 | 0 | 2022-01-10 |  | 40% | 0.4% | 100% | 0.4% | 0% | 0% | bar: 2019.12 9
| Schedule Planning | Develop Schedule(WBS) |  |  | Planning | Progress | 1 | 1 | 0 | 2022-01-10 | 2022-01-11 | 2022-01-19 |  | 40% | 0.4% | 100% | 0.4% | 0% | 0% | bar: 2019.12 6; 2019.12 9
| Start | Kick-off Meeting |  |  | JDT / Planning | Progress | 1 | 1 | 0 | 2022-01-11 | 2022-01-11 | 2022-01-11 |  | 20% | 0.2% | 100% | 0.2% | 0% | 0% | bar: 2019.12 17
소계 | [5 empty] | Progress | 3 | 3 | 0 |  |  | 0 |  | 100% | 1% | 100% | 1% | 0% | 0%
Analytics | 5% | [10 empty] | 0
| Collect Defining | Requirement Meeting |  |  | Planning | Progress | 1 | 1 | 0 | 2021-12-10 | 2022-01-28 | 0 |  | 20% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2019.12 9 to 2019.12 13; 2019.12 16 to 2019.12 20; 2019.12 23 to 2019.12 24; 2019.12 26 to 2019.12 27; 2019.12 30
|  | Information Architecture (PC&Tablet&Tablet/Mobile Web/Language) |  |  | Planning | Progress | 1 | 1 | 0 | 2022-01-11 | 2022-01-28 | 0 |  | 15% | 1% | 100% | 1% | 0% | 0% | bar: 2019.12 9 to 2019.12 10
|  | Wireframe - PC master : Main 1 Types / Sub Page 1 Types |  |  | Planning | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2019.12 11 to 2019.12 13; 2019.12 16 to 2019.12 20
| GUI Design Defining | Concept Benchmarking |  |  | Designer | Progress | 1 | 1 | 0 | 2022-01-11 | 2022-01-21 | 0 |  | 15% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2019.12 9 to 2019.12 13
|  | Design Draft - PC master : Main Page 1 Types / Sub Page 1 Types |  |  | Designer | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | bar: 2019.12 16 to 2019.12 20; 2019.12 23 to 2019.12 24; 2019.12 26 to 2019.12 27; 2019.12 30; 2020.01 2 to 2020.01 3
|  | Design Review / Confirm |  |  | Designer | Progress | 1 | 1 | 0 | 2022-01-10 | 2022-01-25 | 0 |  | 15% | 1% | 100% | 1% | 0% | 0% | bar: 2020.01 6; 2020.01 8
| Programing Defining | Analysis of System Environment |  |  | Planning / developer | Progress | 1 | 1 | 0 | 2022-02-03 | 2022-02-14 | 0 |  | 15% | 0.75% | 100% | 0.75% | 0% | 0% | bar: 2019.12 11 to 2019.12 13; 2019.12 16 to 2019.12 20; 2019.12 23 to 2019.12 24
|  | Define and Set Up of Development Server Environment |  |  | developer | Progress | 1 | 1 | 0 | 2022-02-03 | 2022-02-14 | 0 |  | 10% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2019.12 11 to 2019.12 13; 2019.12 16 to 2019.12 20; 2019.12 23 to 2019.12 24
Subtotal | [5 empty] | Progress | 7 | 7 | 0 |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Design | 35% | bar: 2019.12 16
| Planning Design | Confirm IA Lables & Drop Down Menu |  |  | JDT / Planning | Progress | 1 | 1 | 0 | 2022-01-11 | 2022-01-28 | 0 |  | 0.2% | 0.07% | 100% | 0.07% | 0% | 0%
|  | Collect Contents by JDT Staffs(Master Contents) |  |  | JDT / Planning | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF! | bar: 2019.12 27; 2020.01 13; 2020.01 31
|  | Contents Translation(Korean) |  |  | JDT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  | Contents Translation(Simplified Chines) |  |  | JDT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  | Contents Translation(Traditional Chinese) |  |  | JDT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  | Contents Translation(Japanese) |  |  | JDT | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
Storyboard(PC - Korean) | bar: 2019.12 23 to 2019.12 24; 2019.12 26 to 2019.12 27; 2019.12 30; 2020.01 2 to 2020.01 3; 2020.01 6 to 2020.01 8
|  |  | Offers |  | 김소은 | Progress | 1 | 1 | 0 | 2022-01-11 | 2022-01-12 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Hotel |  | 김현주 | Progress | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2020.01 6 to 2020.01 10; 2020.01 13 to 2020.01 17
|  |  | Dining |  | 강주희 | Progress | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 | 0 |  | 1.5% | 0.525% | 100% | 0.525% | 0% | 0%
|  |  | Entertainment |  | 김지향 | Progress | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | About us |  | 김소은/김현주 | Progress | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Reservation |  |  | Progress | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | Progress | 1 | 1 | 0 | 2022-01-12 | 2022-01-21 | 0 |  | 0.25% | 0.0875% | 100% | 0.0875% | 0% | 0%
|  | Storyboard(Mobile Web - Korean) | Main |  |  | Progress | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0% | bar: 2020.01 16 to 2020.01 17; 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31
|  |  | Offers |  | 김소은 | Progress | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Hotel |  | 김현주 | Progress | 1 | 1 | 0 | 2022-01-24 | 2022-01-27 | 0 |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(PC - Master Contents) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(Mobile Web- Master Contents) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(PC - Simplified Chinese) | Main |  |  | Progress | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | Progress | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(Mobile Web - Simplified Chinese) | Main |  |  | Progress | 1 | 1 | 0 | 2022-02-14 | 2022-02-18 |  |  | 1% | 0.35% | 100% | 0.35% | 0% | 0%
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(PC - Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(Mobile Web- Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(PC - Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Storyboard(Mobile Web- Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  | 김소은 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  | 김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  | 강주희 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  | 김지향 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  | 김소은/김현주 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1.5% | 0.525% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.25% | 0.0875% | #REF! | #REF! | #REF! | #REF!
|  | Admin defintion |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.07% | #REF! | #REF! | #REF! | #REF! | bar: 2020.01 20 to 2020.01 23
| GUI Design | Develop GUI design guide(PC&Tablet/Mobile Web) |  |  | 디자이너 | Progress | 1 | 1 | 0 | 0 | 0 |  |  | 0.8% | 0.28% | 100% | 0.28% | 0% | 0% | bar: 2020.01 7 to 2020.01 10
| Publishing Design | All website pages Guide(PC&Tablet/Mobile Web) |  |  | 퍼블리셔 | Progress | 1 | 1 | 0 | 0 | 0 |  |  | 0.8% | 0.28% | 100% | 0.28% | 0% | 0% | bar: 2020.01 14 to 2020.01 17
| Developing Design | Start |  |  | 개발 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.175% | #REF! | #REF! | #REF! | #REF! | bar: 2020.01 2 to 2020.01 3; 2020.01 6 to 2020.01 10; 2020.01 13 to 2020.01 15
|  | Design for ER Diagram/ |  |  | 개발 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 1% | 0.35% | #REF! | #REF! | #REF! | #REF! | bar: 2020.01 2 to 2020.01 3; 2020.01 6 to 2020.01 10; 2020.01 13 to 2020.01 15
Subtotal | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 100% | 35% | #REF! | #REF! | #REF! | #REF!
Developing | 50%
GUI Design
|  | Multi-lingual Example Guide(PC&Tablet/Mobile Web) |  |  |  | Progress | 8 | 8 | 0 | 0 | 0 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
Design for GUI of all web-pages (PC - Korean) | bar: 2020.01 13 to 2020.01 17; 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Design for GUI of all web-pages (Mobile Web - Korean) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF! | bar: 2020.01 16 to 2020.01 17; 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31
|  |  | Offers |  |  | Progress | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.3% | 0.15% | 100% | 0.15% | 0% | 0%
|  |  | Hotel |  |  | Progress | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Dining |  |  | Progress | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Entertainment |  |  | Progress | 1 | 1 | 0 | 2022-02-14 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual GUI Desing (PC - Master Contents) | Main |  |  | Progress | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | Progress | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | Complete | 0 | 0 | 0 | 0 | 0 |  |  | 0.5% | 0.25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Other |  |  | Progress | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0%
|  | Multi-lingual GUI Desing (Mobile Web- Master Contents) | Main |  |  | Progress | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | Progress | 1 | 1 | 0 | 2022-02-28 | 2022-03-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual GUI Desing (PC - Simplified Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual GUI Desing (Mobile Web- Simplified Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual GUI Desing (PC - Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual GUI Desing (Mobile Web - Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual GUI Desing (PC - Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual GUI Desing (Mobile Web - Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
Pulishing | bar: 2020.01 13 to 2020.01 17; 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31
|  | Web Pages Publishing (PC - Master Contents) | Main |  |  | Progress | 1 | 1 | 0 | 2022-02-04 | 2022-02-04 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Web Pages Publishing (Mobile Web - Master Contents) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF! | bar: 2020.01 16 to 2020.01 17; 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31
|  |  | Offers |  |  | Progress | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.3% | 0.15% | 100% | 0.15% | 0% | 0%
|  |  | Hotel |  |  | Progress | 1 | 1 | 0 | 2022-02-21 | 2022-02-25 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | Complete | 0 | 0 | 0 | 0 | 0 |  |  | 0.5% | 0.25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Other |  |  | Progress | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0%
|  | Multi-lingual Publishing (PC - Korean) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | Progress | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.5% | 0.25% | 100% | 0.25% | 0% | 0%
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | Progress | 1 | 1 | 0 | 2022-03-07 | 2022-03-11 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0%
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (Mobile Web - Korean) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (PC - Simplified Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (Mobile Web - Simplified Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (PC - Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (Mobile Web - Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (PC - Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (Mobile Web - Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
Programing | bar: 2020.01 13 to 2020.01 17; 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31
|  | Front-end Programing (PC - Master Contents) | main |  |  | Progress | 5 | 5 | 0 | 2022-03-10 | 2022-04-08 |  |  | 0.1% | 0.05% | 100% | 0.05% | 0% | 0%
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | Progress | 5 | 5 | 0 | 2022-03-28 | 2022-04-15 |  |  | 0.3% | 0.15% | 100% | 0.15% | 0% | 0%
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Front-end Programing (Mobile Web - Master Contents) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF! | bar: 2020.01 16 to 2020.01 17; 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (PC - Korean) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (Mobile Web - Korean) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (PC - Simplified Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Publishing (Mobile Web - Simplified Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Front-end Progrmaing (PC -Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Front-end Progrmaing (Mobile Web - Traditional Chinese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Front-end Progrmaing (PC -Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Multi-lingual Front-end Progrmaing (Mobile Web -Japanese) | Main |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Social Review / Chatbot / e-Concierge |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Offers |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | Hotel |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.5% | 0.25% | #REF! | #REF! | #REF! | #REF!
|  |  | Dining |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.6% | 0.3% | #REF! | #REF! | #REF! | #REF!
|  |  | Entertainment |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | What's on now |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Dream Itinerary |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.3% | 0.15% | #REF! | #REF! | #REF! | #REF!
|  |  | About us |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Reservation |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  | Dream Reward Club |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sing In |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Find User Information |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  |  |  | Sign Up |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  |  | My Page |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.2% | 0.1% | #REF! | #REF! | #REF! | #REF!
|  |  | Other |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | 0.1% | 0.05% | #REF! | #REF! | #REF! | #REF!
|  | Back-end Developing |  |  | 개발 | Progress | 8 | 8 | 0 | 2022-02-21 | 2022-04-15 |  |  | 1% | 0.5% | 100% | 0.5% | 0% | 0% | bar: 2020.01 20 to 2020.01 23; 2020.01 28 to 2020.01 31; 2020.02 3 to 2020.02 7; 2020.02 10 to 2020.02 14; 2020.02 17 to 2020.02 21; 2020.02 24 to 2020.02 28; 2020.03 2 to 2020.03 6; 2020.03 9 to 2020.03 13; 2020.03 16 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.03 30; 2020.04 1 to 2020.04 3; 2020.04 6 to 2020.04 10; 2020.04 13 to 2020.04 14; 2020.04 16 to 2020.04 17; 2020.04 20 to 2020.04 24; 2020.04 27 to 2020.04 29; 2020.05 1; 2020.05 4; 2020.05 6 to 2020.05 8; 2020.05 11 to 2020.05 15; 2020.05 18 to 2020.05 22; 2020.05 25 to 2020.05 29
Subtotal | [5 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | 100% | 50% | #REF! | #REF! | #REF! | #REF!
Testing/Inspection | 5%
| 1st test | Making A User Test Scenario(PC - Korean) |  |  |  | Progress | 1 |  |  | 2020-03-09 | 2022-03-18 |  |  | 5% | 0.25% | 0% | 0% | 0% | 0% | bar: 2020.03 9 to 2020.03 10; 2020.05 25 to 2020.05 29
|  | Making A User Test Scenario(Mobile - Korean) |  |  |  | Progress | 1 |  |  | 2020-03-09 | 2022-03-18 |  |  | 5% | 0.25% | 0% | 0% | 0% | 0%
|  | Integration Tests (by scenario) |  |  |  | Progress | 1 |  |  | 2020-03-11 | 2022-04-15 |  |  | 20% | 1% | 0% | 0% | 0% | 0% | bar: 2020.03 11 to 2020.03 13; 2020.03 16 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.06 4 to 2020.06 5; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26
|  | Debugging |  |  |  | Progress | 1 |  |  | 2020-03-11 | 2022-04-22 |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 11 to 2020.03 13; 2020.03 16 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.06 4 to 2020.06 5; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26
|  | Prepare Open Contents(e.g. Promotion Banners) |  |  |  | Progress | 10 |  |  | 2020-03-09 | #REF! |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 9 to 2020.03 13; 2020.03 16 to 2020.03 19; 2020.06 1 to 2020.06 5; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 16
| 1st Beta Open | Security check / Modify |  |  |  | Progress | 1 |  |  | 2020-03-19 | #REF! |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 19 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26
|  | Beta Test / Debugging |  |  |  | Progress | 1 |  |  | 2020-03-16 | #REF! |  |  | 15% | 0.75% | 0% | 0% | 0% | 0% | bar: 2020.03 16 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.03 30; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26; 2020.06 29
|  | JDT Internal Open |  |  |  | Progress | 1 |  |  | 2020-03-20 | #REF! |  |  | 15% | 0.75% | 0% | 0% | 0% | 0% | bar: 2020.03 20; 2020.06 12
|  | JDT Internal Open |  |  |  | Progress | 1 |  |  | 2020-03-20 | #REF! |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 27; 2020.06 22
| 2nd test | Making A User Test Scenario(PC - Korean) |  |  |  | Progress | 1 |  |  | 2020-05-25 | #REF! |  |  | 5% | 0.25% | 0% | 0% | 0% | 0% | bar: 2020.03 9 to 2020.03 10; 2020.05 25 to 2020.05 29
|  | Making A User Test Scenario(Mobile - Korean) |  |  |  | Progress | 1 |  |  | 2020-05-25 | #REF! |  |  | 5% | 0.25% | 0% | 0% | 0% | 0%
|  | Integration Tests (According to Scenario) |  |  |  | Progress | 1 |  |  | 2020-06-04 | #REF! |  |  | 20% | 1% | 0% | 0% | 0% | 0% | bar: 2020.03 11 to 2020.03 13; 2020.03 16 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.06 4 to 2020.06 5; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26
|  | Bugfix |  |  |  | Progress | 1 |  |  | 2020-06-04 | #REF! |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 11 to 2020.03 13; 2020.03 16 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.06 4 to 2020.06 5; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26
|  | Prepare Open Contents(e.g. Promotion Banners) |  |  |  | Progress | 10 |  |  | 2020-06-01 | #REF! |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 9 to 2020.03 13; 2020.03 16 to 2020.03 19; 2020.06 1 to 2020.06 5; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 16
| 2nd Beta Open | Security Check / Modify |  |  |  | Progress | 1 |  |  | 2020-06-15 | #REF! |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 19 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26
|  | Beta Test / Debugging |  |  |  | Progress | 1 |  |  | 2020-06-08 | #REF! |  |  | 15% | 0.75% | 0% | 0% | 0% | 0% | bar: 2020.03 16 to 2020.03 20; 2020.03 23 to 2020.03 27; 2020.03 30; 2020.06 8 to 2020.06 12; 2020.06 15 to 2020.06 19; 2020.06 22 to 2020.06 26; 2020.06 29
|  | JDT Internal Open |  |  |  | Progress | 1 |  |  | 2020-06-12 | #REF! |  |  | 15% | 0.75% | 0% | 0% | 0% | 0% | bar: 2020.03 20; 2020.06 12
|  | JDT Confirm |  |  |  | Progress | 1 |  |  | 2020-06-12 | #REF! |  |  | 10% | 0.5% | 0% | 0% | 0% | 0% | bar: 2020.03 27; 2020.06 22
Subtotal | [5 empty] | Progress | 18 | 0 | 0 |  |  |  |  | 100% | 5% | 0% | 0% | 0% | 0%
Closing | 4%
| Open | 1st Open (2020.03.31) |  |  |  | Progress | 1 |  |  | 2020-03-31 | 2022-04-25 |  |  | 20% | 0.8% | 0% | 0% | 0% | 0% | bar: 2020.03 31
|  | 2nd Open (2020.06.30) |  |  |  | Progress | 1 |  |  | 2020-06-30 | #REF! |  |  | 20% | 0.8% | 0% | 0% | 0% | 0% | bar: 2020.06 30
| Completion report | Writing for completion Report |  |  | 기획 | Progress | 1 |  |  | 2020-07-06 | 2022-02-15 |  |  | 5% | 0.2% | 0% | 0% | 0% | 0%
|  | Completion report |  |  | 기획 | Progress | 1 |  |  | 2020-07-10 | 2022-05-06 |  |  | 10% | 0.4% | 0% | 0% | 0% | 0%
| Education and training | Writing for web style guide |  |  | 디자인 | Progress | 1 |  |  | 2020-06-24 | #REF! |  |  | 10% | 0.4% | 0% | 0% | 0% | 0% | bar: 2020.06 24 to 2020.06 26; 2020.06 29; 2020.07 1 to 2020.07 3
|  | Writing for manuals of users and administrators |  |  | 기획/개발/퍼블리싱 | Progress | 1 |  |  | 2020-06-24 | #REF! |  |  | 10% | 0.4% | 0% | 0% | 0% | 0% | bar: 2020.06 24 to 2020.06 26; 2020.06 29; 2020.07 1 to 2020.07 3
|  | Reporting Meeting |  |  | 기획/개발/퍼블리싱 | Progress | 1 |  |  | 2020-07-06 | #REF! |  |  | 10% | 0.4% | 0% | 0% | 0% | 0% | bar: 2020.07 6 to 2020.07 7
| Output production | Submit an output |  |  | 기획/개발/디자인/퍼블리싱 | Progress | 5 |  |  | 2020-06-24 | 2022-05-06 |  |  | 5% | 0.2% | 0% | 0% | 0% | 0% | bar: 2020.06 24 to 2020.06 26; 2020.06 29; 2020.07 1 to 2020.07 2; 2020.07 6 to 2020.07 7
| Systems stability | Website monitoring |  |  | 기획/개발/디자인/퍼블리싱 | Progress | 1 |  |  | 2020-07-01 | 2022-05-06 |  |  | 10% | 0.4% | 0% | 0% | 0% | 0% | bar: 2020.07 1 to 2020.07 3; 2020.07 6 to 2020.07 10; 2020.07 13 to 2020.07 17; 2020.07 20 to 2020.07 24
Subtotal | [5 empty] | Progress | 13 | 0 | 0 |  |  |  |  | 100% | 4% | 0% | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Process Rate Total | [13 empty] | #REF! |  | #REF! |  | #REF! |  | 2020.04 2: #DIV/0!; 2020.04 4: #DIV/0!; 2020.04 6: #DIV/0!
1/8 디자인 시안, BI/BX 확정
12/16 IA, 레이블링 확정
12/27 컨텐츠 수급 완료
1/13 다국어 번역 완료(1차 PC기준)
1/31 PC&Table 디자인 완료(1차 오픈)
3/31 1차 오픈(2개 언어)
3/20 JDT 내부 오픈(2개 언어)
3/27 오픈컨텐츠 최종 확인 (2개 언어)
6/12 JDT 내부 오픈(3개 언어)
3/27 오픈컨텐츠 최종 확인 (3개 언어)
6/30 2차 오픈(3개 언어)
1/31 다국어 번역 완료(2차 PC기준)
4/10 추가 컨텐츠 번역 건
4/10 추가 컨텐츠 번역 건
1/31 PC&Table 디자인 완료(1차 오픈)
4/10 추가 컨텐츠 번역 건
1/31 PC&Table 디자인 완료(1차 오픈)
4/10 추가 컨텐츠 번역 건
3/31 1차 오픈(2개 언어)
3/20 JDT 내부 오픈(2개 언어)
6/12 JDT 내부 오픈(3개 언어)